## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | team-project-2201-swen-261-03-a-tomato
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | ZE 9/29
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | ZE 9/29
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | ZE 9/29
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | ZE 9/29
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | ZE 9/29
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | ZE 9/29
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | ZE 9/29
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  |  | Pass | ZE 10/19
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  |  | Pass | ZE 10/19
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  |  | Fail | ZE 10/19
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  |  | Pass | ZE 10/19
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  |  | Pass | ZE 10/19
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  |  | Pass | ZE 10/19
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  |  | Pass | ZE 10/19
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  |  | Pass | ZE 10/19
As a Player I want my checker to become a King if it reaches the end of the board so that I have an improved piece. | Given it is my turn when I move to the end of the board then I gain an improved piece.
Given I reached the end of the boardwhen I gain an improved piece then replace the piece that made it to the end with an improved piece.
Given I have an improved piece then I am allowed to move my piece backward or forward.
As a Player I want to move my checkers diagonally forward so that I can advance my checkers. | Given it is my turn when I select a square to move to then my piece moves to that square. |  |  | Pass | ZE 10/21
| Given it is my turn when I select a square that has another piece on it then I cannot move to that square. |  |  | Pass | ZE 10/21
| Given it is not my turn when my opponent makes a move then it should be shown on the board. |  |  | Pass | ZE 10/21
As a Player I want to be able to jump over an opponent player’s piece so that I can take that piece. | Given it is my turn when select a space diagonally behind my opponent then to take my opponent's piece. |  |  | Pass | ZE 10/21
| Given there is a capture available for me whenI make a move then the move removes the opponent piece. |  |  | Pass | ZE 10/21
As a Player I want to be able to jump over multiple opponent pieces so that I can take multiple pieces in one turn. | Given there are multiple jump moves available when make a jump move then my turn resets allowing me to make another jump move.
As a Player I want to resign the game I am playing so that I am done playing. | Given it is my turn when I decide to resign then my opponent wins the game.
As a Player I want to create games so that I can play checkers. | Given an opponent is available to play when choose an opponent then a game to be created against the selected opponent.
As a Player I want to select between games that I am playing so that I can make a move for that game. | Given I have multiple games that it is my turn when select a game then I am put in that game.
Given It is my turn when am in a game then I can make a move.
Given It is not my turn when move a piece then I cannot place the piece.
As a Player I want to Sign-out so that I am not selectable to play in games. | Given I am logged in when I click sign-out then I am no longer signed in.